SMART PARKING SYSTEM

Small introduction  :

We Have to address the significant parking congestion for the “Infra tech”park management for parking the Employees vehicles. So, we want to build the parking area.(Budget Cap is at $5000 USD)

Objective :

Within $5000 USD ( INDIAN RUPEES APPROX… –₹451,000 INR ) We want to build the document for the automated System to Guide Drivers to available Spots effectively

We use only specific Infrastructure like…(Older model , low resolution security cameras , Basic barrier Gates etc)

## Detailed 14-Day Execution Plan :

Total Budget: USD 5,000 (≈ INR 4,50,000)
            Delivery Model: Full operational deployment

Days 1–2: Requirements Lock & Asset Validation

During the first two days, the consultant will work closely with stakeholders to confirm and formally document the operational objectives, success criteria, and non-negotiable constraints of the Smart Parking System. Legal and compliance validation for the use of video analytics will be verified to ensure uninterrupted production usage. All existing camera feeds will be inventoried and tested for accessibility, stability, and basic visual quality using live RTSP streams. The parking layout will be mapped against actual camera coverage to determine which areas can be reliably monitored. Based on visibility and camera angles, a final decision will be made on whether detection will operate at space level or zone level, and any low-visibility or unusable camera views will be explicitly excluded to prevent downstream rework.

Cost: USD 600 (≈ INR 54,000)

Days 3–4: System Architecture & Configuration Design

In this phase, a complete production-grade system architecture will be designed, covering computer vision processing, backend services, and driver guidance interfaces. Regions of interest will be logically defined for each usable camera feed based on the parking layout. Technology choices will be finalized with a strong preference for lightweight, open-source components to control costs. Fallback and degradation rules will be formally designed to ensure the system remains operational even when individual cameras fail or detection confidence drops.

Cost: USD 700 (≈ INR 63,000)

Days 5–6: Video Ingestion Pipeline Implementation

Over these two days, a stable and efficient video ingestion pipeline will be implemented to reliably consume live streams from all selected cameras. Frame sampling will be configured at a low but sufficient rate to reduce compute costs while maintaining operational accuracy. Basic preprocessing will be applied to accommodate low-resolution feeds, and automated health checks will be added to detect stream interruptions. By the end of this phase, continuous video flow into the system will be established.

Cost: USD 700 (≈ INR 63,000)

Days 7–8: Occupancy Detection & Core Logic Development :

These days focus on the core intelligence of the system. Object detection logic will be implemented within the predefined regions of interest to determine whether parking spaces or zones are occupied or free. Confidence scoring and temporal smoothing rules will be applied to reduce false detections caused by shadows, occlusions, or lighting changes. Zone-level aggregation logic will be finalized to ensure reliable availability reporting even when space-level accuracy is constrained by camera quality.

Cost: USD 900 (≈ INR 81,000)

Days 9–10: Availability Aggregation :

During this phase, backend services will be developed to aggregate occupancy data from all camera feeds into a single source of truth. A lightweight database will track real-time availability states without storing unnecessary historical video data. APIs will be exposed for driver guidance interfaces and operational dashboards. Fail-safe mechanisms will be implemented so that temporary camera outages do not result in incorrect availability information being presented to users.

Cost: USD 800 (≈ INR 72,000)

Days 11–12: Driver Guidance Interface :

In these two days, the system’s outputs will be made visible and usable. A web-based, mobile-friendly interface will be deployed to display real-time parking availability for drivers and operators. If required, simple rule-based logic will be integrated with existing barrier gates to restrict entry when parking reaches defined capacity thresholds, while always preserving manual override capability. The focus will remain on usability, clarity, and operational reliability rather than advanced visual design.

Cost: USD 800 (≈ INR 72,000)

Days 13–14: Stabilization, Training & Production Go-Live

The final phase will be dedicated to system stabilization and operational readiness. End-to-end testing will be conducted during different times of day to validate accuracy and responsiveness under real conditions. Detection thresholds and rules will be fine-tuned based on observed behavior. A focused training session will be delivered to operational staff, and complete system documentation will be handed over. The system will then be formally placed into production use.

Cost: USD 500 (≈ INR 45,000)

Overall  Cost =USD(600+700+700+800+900+800+500)

=$5000 USD( 4,50,000  INR )

Conclusion :

The Smart Parking System project successfully delivers a cost-effective and operational solution by utilizing existing camera infrastructure and optimized computer vision techniques within strict time and budget constraints. The structured execution plan ensures reliable parking availability detection, improved space utilization, and reduced driver search time without requiring new hardware. This project also establishes a scalable foundation for future enhancements and intelligent parking management.